## Add event-Edit Event
ebooking.deaninfotech
| start date | 2014-12-15
| Module | Add event
Sno | Requirement | Output | Status | Done By | Date | Test Review
1 | when you select start date 12/31/2014 then end date should be 12/31/2014 or greater than this.all the date before 12/31/2014 should be disabled in end date | but now I can select previous end date in comparision to start date | Complted | Shekhar Sharma | 2014-12-16 | Working fine
2 | if auditorium and farm housing is booking on 12/31/2014 and then if we want to book again auditorium and farm house on this date then a message screen should we displayed that auditorium and farm house is booking on this date. | No Message is displayed. | Completed/19-12-2104 | Shekhar Sharma |  | Pending some test cases not work
3 | suppose if you select start date as 12/27/2014 and end date as 12/28/2014 now if you erase the start date and change it as 29/12/2014.now start date is 29/12/2014 and end date is 28/12/2014. This couldn't be happen. | But this happens. | Completed | shekhar sharma | 2014-12-16 | Working fine
4 | there should be time format column or validation in Time text box. It should take proper time entry | but know it did not take proper time .if you type 5 then it take as it is.. | Completed/ | Shekhar Sharma |  | pending validation part
5 | in add clients column we have to apply validation that duplicates clients can't be added.if we insert same information then on click of checkbox Add as new client a message appears that this client already exist. | but now it takes duplicate clients. | Completed/22-12-2014
6 | In manage column Promoters name should be clients or vice versa. | it seems confusing | done but upload later | shekhar sharma | 2014-12-16
7 | there is no need to schedule menu in header.instead of this we have to place day,month and year tab on master page. | No need of schedule menu. | WIP
8 | if we did not select the date in reminder checklist option then bydefault date column takes no date | bydefault if we do not select any date then it take 1/1/1900 as default date.remove this. | no in use now
9 | need to work on add notification as described by sir | need to work | no in use now
10 | need to work on reminder checklist as described by sir | need to work | no in use now
11 | need to work on add inventory as described by sir | need to work | WIP
12 | on manage tab when we click on promoters page then on search box text did not visible and also searching is not fine | need to work | Done on all pages designing part is left | shekhar sharma | 2014-12-16 | Working fine
13 | check box position changes with all validation | change position appliy all validation as discussed | completed | Shekhar Sharma | 2014-12-17 | working fine
14 | Start Time and end time functionality add with validation | new functionality | completed/22-12-2014 | shekharsharma |  | pending validation part
15 | if we check send mail to client true then send mail else no | add on | complated/19-12-2014 | shekhar sharma |  | mail not coming
16 | 500 internal server error | after few min shows 500 internal server error | complated/23-12-2014 | shekhar sharma |  | solved
17 | added new functionality on More Info in which detals of Venue/Assert information between date | show popup about assert/venue betwewn date | complated/25-12-2014 | shekhar sharma
18 | added new Functionality Start time and End Time | add start time and end time with all validation | complated/28-12-2014 | shekhar sharma
19 | Add Client Module updated | add two radio button new client or exists client | complated/28-12-2014 | shekhar sharma
20 | During add new client check fname,lnameand email id already exists then don’t add or change info and check again | check client information | complated/29-12-2014 | shekhar sharma
21 | add invoice new functionaly add add new pdf on add event page | add invoice and add in dropdown | complated/31-12-2014 | shekhar sharma
22 | replace reminder checklist | replace reminde checklist added inventory | complated/02-1-2014 | shekhar sharma
23 | added new functionality Add inventory | in new table inventory information | complated/3-1-2014 | shekhar sharma
24 | Show inventorybalance infomation | remove this information will done later | complated/3-1-2014 | shekhar sharma
25 | mail sending information for client | send mail to client id checkbox is checked | complated/43-1-2014 | shekhar sharma
26 | mail sending information for Event Owner | send mail to event owner | complated/5-1-2014 | shekhar sharma
27 | replace check inventory information | remove inventory balance information | complated/09-1-2014 | shekhar sharma
28 | add invoice on submit | add invoice on final submit | complated/09-1-2014 | shekhar sharma
29 | chekck all validation if add new client is check | add new client id any of one is fill like fname.or lastname or emailid | complated/12-1-2014 | shekhar sharma
30 | spacing between all alert message's | spancing between all alert msgs | complated/12-1-2015 | shekhar sharma
| in notifaction remove date column | only add notification and description. | complated/12-1-2015 | shekhar sharma

## Report
ebooking.deaninfotech
| start date | 2014-12-15
| Module | Report
Sno | Requirement | Output | Status | Done By | Date | Test Review
1 | Report download pdf ground name display not id | bug ground id displayed | completed/22-12-2014 | shekhar sharma

## Event Page
ebooking.deaninfotech
| start date | 2015-01-07
| Module | Add event
Sno | Requirement | Output | Status | Done By | Date | Test Review | Condition
1 | When number of events are more in the popup then need to show close button | close button is dissappear | need to work | done By shekhar | 2014-01-08 | done
2 | there is a 500 error internal server error on page after some time | 500 internal server error | need to work | Please specify on which condition and duration or time. | 2014-01-08 | check the condition | when page is open for a long time i.e for 15-20 min after that when we refresh the page 500 internal server eror comes
3 | for mail functionality need admin panel | no admin panel exist | need to work | wip |  | ok
4 | event Title is compulsory on add event page | right now page is submitted without event name | need to work | done By shekhar | 2014-01-08 | done
5 | when we click on venues/assets checkboxes it takes much time | page reloaded after checking on checkbox | need to work | Functionalty review later. |  | ok
6 | in add notificaation when we add notification gridview column names are aligned according to data | gridview column name are not aligned | need to work | done ny shekhar | 2014-01-08 | done
7 | In pop up we need one extra column status.so that while booking event can see the event is on hold or confirmed | status column not appear | need to work | Done By shekhar | 2014-01-08 | done
8 | after message is displaying on the top if we change the date less than start date or vice versa then according to requirement message should be cleared | message not cleared.. | need to work
9 | message should be displayed."End date should be equal or greater than start date." | "End date should be equal or greater then start date" | check the spelling then and apply fullstop at the end.
10 | Message should be displayed."Start date should be equal or lesser than end date." | "Start date should be equal or lesser then end date"" | check the spelling then and apply fullstop at the end.
11 | Message space"auditorium is already booked between 2/2/2015 and 2/20/2015 moreinfo" are not equal | space between characters should be equal. | check the space
13-01-2014(new)
12 | status is not aligned properly | please aligned the status column
13 | when we select status hold or confirmed and if after that we select "select" then no color should be displayed | but color changes red or green.
14 | after selecting "Add clients" when we click on add invoice then selected radio part button goes to "Add Invoice column".this should not be happen | it happens
15 | Message should be displayed when add duplicate clients "Client already exist :- deepak mittal, d.mittal71@gmail.com." | "Client Already Exists:- deepak mittal d.mittal7@gmail.com"
16 | Message should be displayed"Please select Inventory." | "Please select Inventory.."
17 | Message should be displayed"please enter inventory quantity." | "please enter inventory quantity.."
18 | Description should not be mandatory | but now description is maindatory
19 | in add notification column text box of description is not properly aligned.. | not aligned
20 | In add notification column description should not be maindatory. | but now it is maindatory