## Add event-Edit Event
ebooking.deaninfotech
| start date | 2014-12-15
| Module | Add event
Sno | Requirement | Output | Status | Done By | Date | Test Review
1 | when you select start date 12/31/2014 then end date should be 12/31/2014 or greater than this.all the date before 12/31/2014 should be disabled in end date | but now I can select previous end date in comparision to start date | Complted | Shekhar Sharma | 2014-12-16 | Working fine
2 | if auditorium and farm housing is booking on 12/31/2014 and then if we want to book again auditorium and farm house on this date then a message screen should we displayed that auditorium and farm house is booking on this date. | No Message is displayed. | Completed/19-12-2104 | Shekhar Sharma |  | Fine
3 | suppose if you select start date as 12/27/2014 and end date as 12/28/2014 now if you erase the start date and change it as 29/12/2014.now start date is 29/12/2014 and end date is 28/12/2014. This couldn't be happen. | But this happens. | Completed | shekhar sharma | 2014-12-16 | Working fine
4 | there should be time format column or validation in Time text box. It should take proper time entry | but know it did not take proper time .if you type 5 then it take as it is.. | Completed/ | Shekhar Sharma |  | Working fine
5 | in add clients column we have to apply validation that duplicates clients can't be added.if we insert same information then on click of checkbox Add as new client a message appears that this client already exist. | but now it takes duplicate clients. | Completed/22-12-2014 |  |  | fine
6 | In manage column Promoters name should be clients or vice versa. | it seems confusing | done but upload later | shekhar sharma | 2014-12-16 | fine
7 | there is no need to schedule menu in header.instead of this we have to place day,month and year tab on master page. | No need of schedule menu. | WIP |  |  | fine
8 | if we did not select the date in reminder checklist option then bydefault date column takes no date | bydefault if we do not select any date then it take 1/1/1900 as default date.remove this. | not using |  |  | ok
9 | need to work on add notification as described by sir | need to work | not using |  |  | ok
10 | need to work on reminder checklist as described by sir | need to work | not using |  |  | ok
11 | need to work on add inventory as described by sir | need to work | completed |  |  | ok
12 | on manage tab when we click on promoters page then on search box text did not visible and also searching is not fine | need to work | Done on all pages designing part is left | shekhar sharma | 2014-12-16 | Working fine
13 | check box position changes with all validation | change position appliy all validation as discussed | completed | Shekhar Sharma | 2014-12-17 | working fine
14 | Start Time and end time functionality add with validation | new functionality | completed/22-12-2014 | shekharsharma |  | working fine
15 | if we check send mail to client true then send mail else no | add on | complated/19-12-2014 | shekhar sharma |  | ok
16 | 500 internal server error | after few min shows 500 internal server error | complated/23-12-2014 | shekhar sharma |  | solved
17 | added new functionality on More Info in which detals of Venue/Assert information between date | show popup about assert/venue betwewn date | complated/25-12-2014 | shekhar sharma |  | ok
18 | added new Functionality Start time and End Time | add start time and end time with all validation | complated/28-12-2014 | shekhar sharma |  | ok
19 | Add Client Module updated | add two radio button new client or exists client | complated/28-12-2014 | shekhar sharma |  | ok
20 | During add new client check fname,lnameand email id already exists then don’t add or change info and check again | check client information | complated/29-12-2014 | shekhar sharma |  | ok
21 | add invoice new functionaly add add new pdf on add event page | add invoice and add in dropdown | complated/31-12-2014 | shekhar sharma |  | ok
22 | replace reminder checklist | replace reminde checklist added inventory | complated/02-1-2014 | shekhar sharma |  | ok
23 | added new functionality Add inventory | in new table inventory information | complated/3-1-2014 | shekhar sharma |  | ok
24 | Show inventorybalance infomation | remove this information will done later | complated/3-1-2014 | shekhar sharma |  | ok
25 | mail sending information for client | send mail to client id checkbox is checked | complated/43-1-2014 | shekhar sharma |  | ok
26 | mail sending information for Event Owner | send mail to event owner | complated/5-1-2014 | shekhar sharma |  | ok
27 | replace check inventory information | remove inventory balance information | complated/09-1-2014 | shekhar sharma |  | ok
28 | add invoice on submit | add invoice on final submit | complated/09-1-2014 | shekhar sharma |  | ok
29 | chekck all validation if add new client is check | add new client id any of one is fill like fname.or lastname or emailid | complated/12-1-2014 | shekhar sharma |  | ok
30 | spacing between all alert message's | spancing between all alert msgs | complated/12-1-2015 | shekhar sharma |  | ok
31 | in notifaction remove date column | only add notification and description. | complated/12-1-2015 | shekhar sharma |  | ok
32 | add attachment selecet file and clear file | during the attachment |  |  |  | ok
33 | when file attached upload should be dissabled | attachmented file |  |  |  | ok
34 | clare button only visible when file is attached. | when file is attached. |  |  |  | ok
35 | mail send when admin allowed from admin page checkbox is checked | if check box checked in admin page |  |  |  | ok
36 | mail to client only send when both on event page or admin allowed to send mail | if check box checked in admin page |  |  |  | ok
37 | edit event page show wrong information about status.when we select status as "hold" it shows confirm in edit or update page..(19-03-2015) | status not showing right value… | Done 12-03-2015 | Shekhar Sharma | 2015-03-12 | not done .still shows status as confirmed | I have not seen any bug. Kindly check and try to let me know on which parameter you are geeting this error.
38 | Remove search box from this page(19-03-2015) | no requirement of search on this page | done 19-03-2015 | shekhat sharma
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103

## Admin
ebooking.deaninfotech
| start date | 2014-02-13
| Module | Admin
Sno | Requirement | Output | Status | Done By | Date | Test Review
1 | create admin | admin created with all validation | Complted
2 | edit admin | update admin info from grid | Complted
3 | delete admin | delete admin from grid | Complted
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27

## Reminder
x
ebooking.deaninfotech
start date | 2014-12-15
Module | Reminder
Requirement | Output | Status | Done By | Date | Test Review
mail setup dynamic
checkbox Send Mail to login User/Event Creator | if these check then send mail to event creator | Complted
Mail to Client | if check then send mail client | Complted
Mail to Employee Reminder | if check the send mail to notifiuser | Complted
below these are the scheduler run with in intervel of time
Mail to client bulkinfo |  | Complted
Mail to Client |  | wip
Mail to EmployeE Reminder |  | wip
view and Updatedate mail format | view nad reset the update of mail format | Complted
Send Mail to login User/Event Creator | view nad reset the update of mail format | Complted
Mail to Client | view nad reset the update of mail format | Complted
Mail to Employee Reminder | view nad reset the update of mail format | Complted
Notification [Reminder] | view nad reset the update of mail format | Complted
Send Mail to login User/Event creator | view nad reset the update of mail format | Complted
Mail to Client | view nad reset the update of mail format | Complted
Mail to EmployeE Reminder | view nad reset the update of mail format | Complted

## Report
ebooking.deaninfotech
| start date | 2014-12-15
| Module | Report
Sno | Requirement | Output | Status | Done By | Date | Test Review
1 | Report download pdf ground name display not id | bug ground id displayed | completed/22-12-2014 | shekhar sharma

## Event Page
ebooking.deaninfotech
| start date | 2015-01-07
| Module | Add event
Sno | Requirement | Output | Status | Done By | Date | Test Review | Condition
1 | When number of events are more in the popup then need to show close button | close button is dissappear | need to work | done By shekhar | 2014-01-08 | done
2 | there is a 500 error internal server error on page after some time | 500 internal server error | need to work | Please specify on which condition and duration or time. | 2014-01-08 | check the condition | when page is open for a long time i.e for 15-20 min after that when we refresh the page 500 internal server eror comes
3 | for mail functionality need admin panel | no admin panel exist | need to work | wip |  | ok
4 | event Title is compulsory on add event page | right now page is submitted without event name | need to work | done By shekhar | 2014-01-08 | done
5 | when we click on venues/assets checkboxes it takes much time | page reloaded after checking on checkbox | need to work | Functionalty review later. |  | ok
6 | in add notificaation when we add notification gridview column names are aligned according to data | gridview column name are not aligned | need to work | done ny shekhar | 2014-01-08 | done
7 | In pop up we need one extra column status.so that while booking event can see the event is on hold or confirmed | status column not appear | need to work | Done By shekhar | 2014-01-08 | done
8 | after message is displaying on the top if we change the date less than start date or vice versa then according to requirement message should be cleared | message not cleared.. | need to work |  |  | done
9 | message should be displayed."End date should be equal or greater than start date." | "End date should be equal or greater then start date" | check the spelling then and apply fullstop at the end. |  |  | done
10 | Message should be displayed."Start date should be equal or lesser than end date." | "Start date should be equal or lesser then end date"" | check the spelling then and apply fullstop at the end. | done ,shekhar sharma | 2015-03-09 | done
11 | Message space"auditorium is already booked between 2/2/2015 and 2/20/2015 moreinfo" are not equal | space between characters should be equal. | check the space | done ,shekhar sharma | 2015-03-09 | not done
13-01-2014(new)
12 | status is not aligned properly | please aligned the status column | need to work | done ,shekhar sharma | 2015-03-09 | done
13 | when we select status hold or confirmed and if after that we select "select" then no color should be displayed | but color changes red or green. | need to work | ponit not clear | 2015-03-09 | done
14 | after selecting "Add clients" when we click on add invoice then selected radio part button goes to "Add Invoice column".this should not be happen | it happens | need to work | done ,shekhar sharma | 2015-03-09 | done
15 | Message should be displayed when add duplicate clients "Client already exist :- deepak mittal, d.mittal71@gmail.com." | "Client Already Exists:- deepak mittal d.mittal7@gmail.com" | need to work | done ,shekhar sharma | 2015-03-09 | done
16 | Message should be displayed"Please select Inventory." | "Please select Inventory.." | need to work | done ,shekhar sharma | 2015-03-09 | done
17 | Message should be displayed"please enter inventory quantity." | "please enter inventory quantity.." | need to work | done ,shekhar sharma | 2015-03-09 | done
18 | Description should not be mandatory | but now description is maindatory | need to work | done ,shekhar sharma (it will be mandatory)in case of notification | 2015-03-09 | ok
19 | in add notification column text box of description is not properly aligned.. | not aligned | need to work | done ,shekhar sharma (ita already alinged) kindly send on which part it is not alignd) screen shoot. | 2015-03-09 | done
20 | In add notification column description should not be maindatory. | but now it is maindatory | need to work | done ,shekhar sharma (ita already alinged) kindly send on which part it is not alignd) screen shoot. | 2015-03-09 | done
21 | if we do not select status then on click of more info in pop up status is shown as hold after saving an event. | status column value not right in pop up |  | done ,shekhar sharma | 2015-03-09 | done
22 | if we select status as hold then on click of more info in pop up status is shown as confirm after saving an event. | status column value not right in pop up |  | Done,Shekhar sharma | 2015-03-12 | not done still shows confirmed when select hold
23 | Change the "assert" to "Assets" | spelling mistake |  | Done shekhar sharma | 2015-03-12 | done
24 | more space occur between the messages which are shown during selecting assets | space is not parallel | kindly specfiy on which Assets and date select you get unparalla space | Done,Shekhar sharma | 2015-03-12 | done
25 | in pop up id column is given,but now in id column event title is coming, is this requirement ? I think this id column is not require here and place the hyperlink on event title column(19-03-2015) |  |  | done,shaekhar sharma | 2015-03-19

## Update Event Page
ebooking.deaninfotech
| start date | 2015-01-03
| Module | Update event
Sno | Requirement | Output | Status | Done By |  |  | Reviews
1 | when we reset event then after updating for another event previous event is not shown which is reset | now it's showing reset event | ok
2 | when we click on new client radio button in add clients column pop up is not displaying | pop is going to displayed says nothing | working fine | Done /27-01-2014
3 | on click of reset event start date,enddate,starttime,endtime and status is to be cleared | all the things are not cleared | ok
4 | attach button has no significance there if we do not click on attach button while attaching add invoice attachment is updated | attachment is updated without clicking on attach button | working fine | Done /27-01-2014
5 | description is not maindatory in add inventory | but now this is maindatory | working fine
6 | description is not maindatory in add notification | but now this is maindatory | ok
7 | same pop up messages as described in event page | same pop up messages | need to work | Done | Shekhar | 2015-03-09 | ok

## Promoters
ebooking.deaninfotech
| start date | 2015-03-03
| Module | Promoters Page
Sno | Requirement | Output | Status | Done By | Date | Reviews
1 | On this page Search should be based upon Firstname+Lastname | If we search Firstname+Lastname then search is not fine | Done | Shekhar | 2015-03-03 | Ok
2 | Validation Should not fail on Giving space in textbox | If we Give sapce in textbox then validation fails | Done | Shekahr | 2015-03-03 | Ok
3 | Phone Number should not take an string value | but here it also takes string value | done | Shekhar | 2015-03-03 | Ok
4 | Validation not working fine | red outlining are present after filling the lastname and please remove javascript pop up |  |  |  | ok
5 | after adding new promoter "new Promoter added" is generated after that if we click on add promoter button then validation message is overlap with each other | overlapping of message occouring |  |  |  | ok
6 | When we click on "Add Promoter" Button without filling any information in textboxes then error message is displayed after that if we click on edit hyperlink in gridview then error message should be removed | but now error message is displayed |  |  |  | ok
7 | and also change the message.replace "enter" in the place of "select" | now messages is not right |  |  |  | ok

## Inventory
ebooking.deaninfotech
| start date | 2015-02-26
| Module | Inventory Page
Sno | Requirement | Output | Status | Done By | reviews
1 | In create date column time should be right | time is not right in create date column in gridview |  |  | ok
2 | When we click on "Add Inventory" Button without filling any information in textboxes then error message is displayed after that if we click on edit hyperlink in gridview then error message should be removed | But still show error message |  |  | ok

## Invoice
ebooking.deaninfotech
| start date | 2015-03-03
| Module | Inventory Page
Sno | Requirement | Output | Status | Done By |  | Reviews |  |  |  | Reviews
1 | "Select PDF file first" message should be blank after select file | still present message "Select PDF file first" | done | shekhar | 2015-03-03 | not done | Done | Shekhar | 2015-03-04 | ok
2 | Remarks should be mendatory | but now not maindatory | done | shekhar | 2015-03-03 | ok
3 | Pageload should not be occur on search button click | but now pageload occurs | done | shekhar | 2015-03-03 | ok

## Reports
ebooking.deaninfotech
| start date | 2015-02-26
| Module | Report Page
Sno | Requirement | Output | Status | Done By | Reviews | Done |  |  |  | Reviews |  |  |  | Reviews
1 | Searching should be based upon start date | not showing the events based on start date. |  |  | Not Done | Done | Shekhar | 2015-03-04 | As per test case now its working. | Not done | Done | Shekhar | 2015-03-09 | ok
2 | when notes section is long in gridview then gridview presentation should be fine | but status and export to pdf is not shown when notes is long. |  |  | ok |  |  |  |  | ok
3 | apply the validation on from date and to date text box so that to date is not less than from date etc. | Now we can enter the small date from "from date" |  |  | ok |  |  |  |  | ok
4 | export to pdf is not working,pdf is not downlodable | pdf not working |  |  |  | Done | Shekhar | 2015-03-12 |  | ok
5 | pdf which is downloaded is of 2 page .while in second page no content is there.second page is blank/19-03-2015 | pdf format is not fine |  |  |  | done | shekagr | 2015-03-19 | date of test 19-03-2015

## Venues
ebooking.deaninfotech
| start date | 2015-03-03
| Module | Venues/Assets Page
Sno | Requirement | Output | Status | Done By |  | Reviews
1 | When we click on "Update" Button without filling any information in textboxes then error message is displayed after that if we click on edit hyperlink in gridview then error message should be removed | but error message is displayed | done | shekhar | 2015-03-03 | Ok
2

## Users
ebooking.deaninfotech
| start date | 2015-02-26
| Module | Venues/Assets Page
Sno | Requirement | Output | Status | Done By | Reviews
1 | When we click on "Update" Button without filling any information in textboxes then error message is displayed after that if we click on edit hyperlink in gridview then error message should be removed | but error message is displayed |  |  | Ok
2 | password textbox is of password type. | but now it is text type. |  |  | Ok
3 | when we click on search textbox and press enter button without write anything then a javascript alert message is generated. | pop up is generated |  |  | ok

## AccessInfo
ebooking.deaninfotech
| start date | 2015-03-03
| Module | AccessInfo Page
Sno | Requirement | Output | Status | Done By |  | Reviews | status |  |  | Reviews
1 | if we remove access of all admin pages then admin tab should not be displayed | but now admin tab is displayed after remove all three page access | done | shekhar | 2015-03-03 | Not Working Fine | Done | Shekhar | 2015-03-04 | ok
2 | if we remove access of all Manage pages then Manage tab should not be displayed | but now Manage tab is displayed after remove all page access | done | shekhar | 2015-03-03 | Not Working Fine | done | Shekar | 2015-03-04 | ok

## Home page
ebooking.deaninfotech
| start date | 2015-03-03
| Module | Home Page
Sno | Requirement | Output | Status | Done By | Reviews
1 | on every 5-10 minutes page expires | page expires
2 | sometimes 503 error comes. The service is unavialable | 503 error comes | 503 IS A SERVER ERROR I HAVE SEEN WHEN THIS ERROR ARIES AND WHEN I OPEN WWW.DEANINFOTECH.COM. SAME ERROR CAME. PLEASE MAKE ME COOECT IF I AM WRONG.

## Details
ebooking.deaninfotech
| start date | 2015-03-16
| Module | Details Page
Sno | Requirement | Output | Status | Done By | Reviews
1 | Event Creator Name | name of event creator | completed/16-03-2015 | shekhar sharma | ok
2 | Event Created Date | default created date | completed/16-03-2015 | shekhar sharma | ok
3 | Event Updated By | updated event user name | completed/16-03-2015 | shekhar sharma | ok
4 | Event Updated date | default create date | completed/16-03-2015 | shekhar sharma | ok
5 | Details page show wrong information about status.when we select status as "hold" it shows confirm in Details page.. | status not shownig right value

## popup Schdeule
ebooking.deaninfotech
| start date | 2015-03-19
| Module | Pop UP Schduele
Sno | Requirement | Output | Status | Done By | Reviews
1 | hold events should be red colour in pop up | but now hold events are green | its already working.kindly test again and parameter you are passing.i have not seen any bug. | shekhar sharma/19-03-2015

## Reminder Page
ebooking.deaninfotech
| start date | 2015-03-19
| Module | Reminder Page
Sno | Requirement | Output | Status | Done By | Reviews
1 | schdule popup overlap the page div | overlap the page div |  | shekhar/19-03-2015 | it’s not a functionatily bug.its a design issuse.but I have done it later on it will improve again.